## Main
Scrum Project
Product | Phase 1 Assessment Prototype |  | Product Status | Complete
Active versions |  |  | Sponsor | Company Lockers Pvt. Ltd.
Team
Scrum Master | Brendan Legas |  | Product Owner | Company Lockers
Developers | Brendan Legas |  | Project Champion | Company Lockers
|  |  | Other Stakeholders | Company Lockers
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Develop Prototype | 2021-05-03 | 2021-05-21 | Complete |  | Spr. 1.1 | 2021-05-03 | 2021-05-07 | Complete |  |  | Menu(s)/Basic Navigation
[6 empty] | Spr. 1.2 | 2021-05-10 | 2021-05-14 | Complete |  |  | Add, Delete, Search Files
[6 empty] | Spr. 1.3 | 2021-05-17 | 2021-05-21 | Complete |  |  | Return Files

## Tracker
Sprint Tracker
Week 1
Sprint Id | Backlog Id | Description | Owner | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1.1 | 1 | Create Main Menu | Brendan | Complete | bar: Day 1 to Day 2
1.1 | 2 | Create Sub Menu (Modify Menu) | Brendan | Complete | bar: Day 3 to Week 1 Day 4
1.1 | 3 | Create Loop for navigation | Brendan | Complete | bar: Week 1 Day 5
1.2 | 4 | Add File method | Brendan | Complete | bar: Week 1 Day 1 to Week 1 Day 3
1.2 | 5 | Delet file method | Brendan | Complete | bar: Week 1 Day 4 to Week 1 Day 5; Week 1 Day 1
1.2 | 6 | Search for file method | Brendan | Complete | bar: Week 1 Day 2 to Week 1 Day 3
1.3 | 7 | Return File method | Brendan | Complete | bar: Week 1 Day 4 to Week 1 Day 5